## Sheet1
Table 1.2- BENE
Task |  |  | deliverable | 2003 | [8 empty] | 2004 | [11 empty] | 2005 | [11 empty] | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
ECFA Muon Week |  |  | participations & presentations, slides on www | bar: 2003 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | contributions to Workshop and Proceedings | bar: 2003 jun
preparation of Proposal of Design Studies (DS) and R&D projects |  |  | Proposal Oct 03 | bar: 2003 apr to 2003 oct
CARE and BENE founding meeting at CERN |  |  | participations & presentations, slides on www | bar: 2003 nov
BENE Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
| preparation of contributions to NuFact04 Workshop |  | participation & presentations, slides on www | bar: 2004 mar to 2004 jun
| preparation of writeups for NuFact Proceedings |  | contributions to Proceeedings | bar: 2004 jul to 2004 sep
| preparation of Proposals of additional R&D projects, if required |  | R&D Proposal Oct 04? | bar: 2004 apr to 2004 oct
| preparation of additional JRP proposals (if any) |  | Proposals Apr 05? | bar: 2004 nov to 2005 mar
| preparation of Interim Report (end of first comparative studies) |  | Interim Reports Jun 05 | bar: 2004 apr to 2005 jun
"First set of parameters & Road map to Conceptual Designs" | bar: 2004 apr to 2005 jun
Basic set of parameters: NuFact, Superbeam, Betabeam | bar: 2004 apr to 2005 jun
Define parameters for design of both SPL and RCS | bar: 2004 apr to 2005 jun
Restrict target & collection choices for conceptual design | bar: 2004 apr to 2005 jun
Define measurements with MICE and map to cooling channel design | bar: 2004 apr to 2005 jun
Define parameters for design of muon acceleration and storage | bar: 2004 apr to 2005 jun
Define parameters for design of betabeam components | bar: 2004 apr to 2005 jun
| preparation of NuFact05 & Superbeam Int. Workshop |  | organization of Workshop in Europe | bar: 2005 jan to 2005 jun
| preparation of contributions to NuFact Workshop |  | contributions to Workshop | bar: 2005 mar to 2005 jun
| preparation of writeups for NuFact05 Proceedings |  | contributions to Proceeedings | bar: 2005 jul to 2005 sep
| preparation of Proposals of additional R&D projects, if required |  | R&D Proposal Oct 05? | bar: 2005 apr to 2005 oct
| editing and publication of NuFact05 Proceedings |  | Proceedings end 05 | bar: 2005 oct to 2005 nov
| further comparative study of NuFact, Superbeam, Betabeam |  | Addendum to Interim Report June 06 | bar: 2005 jul to 2006 jun
including specific choice SPL/RCS | bar: 2006 jun
| further comparative study of NuFact, Superbeam, Betabeam |  | Addendum to Interim Report June 07 | bar: 2006 jul to 2007 jun
| contributions to Proposal of a new large underground European Lab |  | Proposal Jul 07 | bar: 2007 feb to 2007 jul
| preparation of final NA and WP reports |  | Final BENE Reports Jun 08 | bar: 2005 jul to 2008 dec
"Status of Physics Studies & Conceptual Designs: Road Map to Technical Designs" | bar: 2005 jul to 2008 dec
NuFact, Superbeam, Betabeam: full comparative study of performance, cost and risk | bar: 2005 jul to 2008 dec
Status & Road Map to complete Technical Design of Driver | bar: 2005 jul to 2008 dec
Status & Road Map to complete Technical Design of Target & Collection | bar: 2005 jul to 2008 dec
Status & Road Map to complete Technical Design of cooling, acceleration & storage | bar: 2005 jul to 2008 dec
Status & Road Map to complete Technical Design of betabeam components | bar: 2005 jul to 2008 dec
| preparation of NuFact08 & Superbeam Int. Workshop |  | organization of Workshop in Europe | bar: 2008 jan to 2008 jun
| draft of final NA and WP reports |  | draft of final report Jun 05 | bar: 2008 feb to 2008 jun
| preparation of writeups for NuFact08 Proceedings |  | contributions to Proceeedings | bar: 2008 jul to 2008 sep
| editing and publication preparation of NuFact08 Proceedings |  | Proceedings end 08 | bar: 2008 oct to 2008 nov
| completion of final general and WP reports |  | Final "Road Map" Report Dec 08 | bar: 2008 jul to 2008 dec
Table 1.2a-PHYSICS WP1
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
ECFA Muon Week |  |  | participations & presentations, slides on www | bar: 2003 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | contributions to Workshop and Proceedings | bar: 2003 jun
preparation of Proposal of Design Studies (DS) and R&D projects |  |  | Proposal Oct 03 | bar: 2003 apr to 2003 oct
CARE and BENE founding meeting at CERN |  |  | participations & presentations, slides on www | bar: 2003 nov
PHYSICS WP1 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
PHYSICS
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
PHYSICS
Define the analysis method for assessing the physics potential of different experiments | bar: 2004 dec; 2005 jun
| Ambiguities, Degeneracies and Correlations in the search for Leptonic CP |  | Organization of Workshop + report | bar: 2004 dec; 2005 jun
| SuperBeams vs. Beta Beams vs NuFact, synergies and priorities |  | Organization of Workshop + report | bar: 2005 jun; 2007 sep
| Preparation of interim (preliminary road map) report |  | Interim Report Jun 05 | bar: 2005 jun
intermediate report
preliminary road map
"Valencia Workshop" on SuperBeams vs. Beta Beams vs NuFact, synergies and priorities (Valencia ?)
"Valencia report" on the same subject
| Optimized parameter list for SuperBeam, BetaBeam and NuFact |  | Reports | bar: 2005 jun; 2007 sep
| Identify and promote a serie of ancillary experiments |  | Report | bar: 2005 jun; 2006 sep
| Close detectors at SuperBeam, BetaBeam and Nufact |  | Report | bar: 2007 feb
| Other physics at the Nufact and Beta Beam |  | Reports | bar: 2004 dec; 2006 feb; 2007 sep
| Monitor the development of the field of nu-physics |  | Neutrino Unbound Web site | bar: 2004 jan to 2008 dec
| Define chapter for final report |  | Report Layout | bar: 2008 mar
A report on an optimized parameter list for SB, BB and NF. Addressing the problems of systematic errors
| present draft of BENE final report |  | Draft Final Report Jun 08 | bar: 2008 jun
| final "roadmap report" |  | Final Report Dec 08 | bar: 2008 dec
Table 1.2b-DRIVER WP2
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
ECFA Muon Week |  |  | participations & presentations, slides on www | bar: 2003 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | contributions to Workshop and Proceedings | bar: 2003 jun
preparation of Proposal of Design Studies (DS) and R&D projects |  |  | Proposal Oct 03 | bar: 2003 apr to 2003 oct
CARE and BENE founding meeting at CERN |  |  | participations & presentations, slides on www | bar: 2003 nov
DRIVER WP2 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
review HIPPI yearly status report |  |  | Final BENE Reports Jun 08 | bar: 2005 jul to 2008 dec
launch full comparative study | bar: 2004 jan
assess HARP data | bar: 2004 jul
review HIPPI status report | review HIPPI status report | bar: 2004 nov
proton source tests, chopper study
tests of RF bunchers
SPL vs RCS: define comparative study
review HIPPI progress report | bar: 2005 mar
accelerating structure 1,
elliptical cavity
SPL vs RCS: preliminary conclusions
review HIPPI progress report | bar: 2005 jul
first RFQ tests, chopper design
beam transport
ECR source modelisation
results of the studies for most elements | bar: 2005 dec
Driver Workshop | bar: 2006 jul
revision of the R&D plans | bar: 2006 dec
Driver Workshop | bar: 2007 jul
revision of the R&D plans | bar: 2007 dec
present draft of final chapter | bar: 2008 jun
Driver Workshop | bar: 2008 jul
final report, driver TDR | bar: 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
| launch working group activities |  | chart of work organization | bar: 2004 jan
| assess preliminary HARP results |  | preliminary report on choice of driver energy | bar: 2004 apr to 2004 jul
| SPL vs RCS: define criteria of comparative study |  | chart of terms of comparison | bar: 2004 aug
| review HIPPI yearly status report |  | report & recommendations | bar: 2004 dec to 2005 jan
| perform preliminary SPL vs RCS comparison |  | preliminary report Jun 05 | bar: 2004 sep to 2005 jun
| first revision of R&D plans |  | revised plan | bar: 2004 sep to 2005 jun
| assess final HARP results |  | final report on choice of driver energy | bar: 2005 apr to 2005 jul
| review HIPPI yearly status report |  | report & recommendations | bar: 2005 dec to 2006 jan
| perform final SPL vs RCS comparison |  | final report on SPL/RCS choice Jun 06 | bar: 2005 jul to 2006 may
| assemble results of the studies for most components |  | report | bar: 2005 oct to 2006 jan
| preparation of Driver Workshop |  | Workshops Jul 06 with Proceedings | bar: 2006 feb to 2006 jul
| revision of status of the studies of components and of R&D plans |  | revised plan | bar: 2006 oct to 2007 jan
| review HIPPI yearly status report |  | report & recommendations | bar: 2006 dec to 2007 jan
| preparation of Driver Workshop |  | Workshops Jul 07 with Proceedings | bar: 2007 feb to 2007 jul
| revision of status of the studies of components and of R&D plans |  | revised plan | bar: 2007 oct to 2008 jan
| review HIPPI yearly status report |  | report & recommendations | bar: 2007 dec to 2008 jan
| prepare draft of final chapter on the status of driver design, |  | draft of chaptere of final report | bar: 2008 jan to 2008 jul
| preparation of Driver Workshop |  | Workshops jul 08 with Proceedings | bar: 2008 feb to 2008 jul
| finalize final chapter on the status of driver design |  | chapter of final report | bar: 2008 aug to 2008 dec
DRIVER WP2 Timetable | deliverable | bar: 2003 nov to 2008 oct
launch working group activities | bar: 2003 nov
assess preliminary HARP results | bar: 2004 may
review HIPPI status report | bar: 2004 sep
SPL vs RCS: define comparative study | Chart of terms of comparison LINAC/RCS | bar: 2005 jan
review HIPPI progress report | Report | bar: 2005 jan
SPL vs RCS: preliminary conclusions | Preliminary report
assess HARP results and
review HIPPI progress report | Report | bar: 2005 may
results of the studies for most elements | Report | bar: 2005 oct
Driver Workshop | Proceedings | bar: 2006 may
revision of the R&D plans | bar: 2006 oct
Driver Workshop | Proceedings | bar: 2007 may
revision of the R&D plans | bar: 2007 oct
present draft of final chapter | Draft report | bar: 2008 apr
Driver Workshop | bar: 2008 may
final report on the driver baseline option | Final Report | bar: 2008 oct
Table 1.2c-TARGET WP3
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
identify nature, location & first list of experiments for a Target Test Area | bar: 2003 apr to 2003 jul
Prepare web page |  |  | Web Page | bar: 2003 apr
prepare Design Study Proposal |  |  | Design Study Proposal to EU | bar: 2003 apr to 2003 oct
| First meeting of Network Target and Collector Sections. |  | Minutes of Target & Collector Sections | bar: 2003 nov
TARGET WP3 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
identify nature, location & first list of experiments for a Target Test Area (TTA) | bar: 2003 apr
start TTA design, prepare proposal | bar: 2003 jun
Proposal TTA | bar: 2003 oct
First meeting of Network Target and Collector Sections. | bar: 2003 nov
Meeting of Target and Collector Sections | bar: 2004 mar
Attend NuFact04 | bar: 2004 jun
Meeting of Target and Collector Sections | bar: 2004 jul
1st International Conference on Targets and Collectors | bar: 2005 mar
Attend NuFact05 | bar: 2005 jun
decide if additional TPW needed | bar: 2005 aug
addendum to TTA Proposal? | bar: 2005 oct
Meeting of Network Target and Collector Sections | bar: 2005 nov
Meeting of Network Target and Collector Sections | bar: 2006 mar
Laboratory Visits by Section Cordinator | bar: 2006 may
Attend NuFact06 | bar: 2006 jun
Report on a specific SuperBeam solutions | bar: 2006 dec
2nd International Conference on Targets and Collectors | bar: 2007 mar
Laboratory Visits by Section Cordinator | bar: 2007 may
Attend NuFact07 | bar: 2007 jun
Meeting of Network Target and Collector Sections | bar: 2007 nov
Report on specific NuFact solutions | bar: 2008 feb
Meeting of Target and Collector Sections. Define chapters for final report | bar: 2008 mar
Attend NuFact07
Meeting of Network Target and Collector Sections | bar: 2008 nov
TARGET WP3 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2004 mar
| Attend NuFact04 |  | participation & contributions to Workshop | bar: 2004 jun
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2004 jul
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2004 nov
1st International Conference on Targets and Collectors | bar: 2004 jan to 2005 mar
| Attend NuFact05 |  | participation & contributions to Workshop | bar: 2005 jun
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2005 jul
Decide if additional Design Study needed | bar: 2005 jul
| Possible addendum to Design Study |  | Possible addendum to Design Study | bar: 2005 jul to 2005 oct
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2005 nov
| Publish Proceedings of 1st International Conference on Targets and Collectors |  | Proc. 1st Int. Conf. on Targets & Collectors | bar: 2005 mar to 2006 jan
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2006 mar
| Attend NuFact06 |  | participation & contributions to Workshop | bar: 2006 jun
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2006 jul
| Report on a specific SuperBeam solutions |  | Report on SuperBeam solutions | bar: 2006 aug to 2006 dec
2nd International Conference on Targets and Collectors | bar: 2006 jan to 2007 mar
| Attend NuFact07 |  | participation & contributions to Workshop | bar: 2007 jun
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2007 jul
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2007 nov
| Publish Proceedings of 2nd International Conference on Targets and Collectors |  | Proc. 2nd Int. Conf. on Targets & Collectors | bar: 2007 mar to 2008 jan
| Report on specific NuFact solutions |  | Report on specific NuFact solutions | bar: 2008 feb
| Meeting of Network Target and Collector Sections. |  | Minutes of Target & Collector Sections | bar: 2008 mar
Define chapters for final report | bar: 2008 mar
| Attend NuFact08 |  | participation & contributions to Workshop | bar: 2008 jun
Draft of final chapters for final report | bar: 2008 jul
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2008 jul
| Meeting of Network Target and Collector Sections |  | Minutes of Target & Collector Sections | bar: 2008 nov
Final Report | bar: 2008 jan to 2009 jan
COLLECTOR WP4 Timetable | deliverable | bar: 2003 nov to 2008 oct
Prepare web page | Web Page
Design Study Proposal | bar: 2003 apr to 2003 aug
Present Design Study Proposal to EU | Design Study Proposal to EU | bar: 2003 aug
First meeting of Network Target and Collector Sections. | bar: 2003 sep
Minutes of Target & Collector Sections | bar: 2003 oct
Meeting of Network Target and Collector Sections | bar: 2004 jan
Minutes of Target & Collector Sections | bar: 2004 feb
Attend NuFact04 | bar: 2004 apr
Meeting of Network Target and Collector Sections | bar: 2004 may
Minutes of Target & Collector Sections | bar: 2004 jun
Meeting of Network Target and Collector Sections | bar: 2004 sep
Minutes of Target & Collector Sections | bar: 2004 oct
1st International Conference on Targets and Collectors | bar: 2003 nov to 2005 jan
Attend NuFact05 | bar: 2005 apr
Meeting of Network Target and Collector Sections | bar: 2005 may
Minutes of Target & Collector Sections | bar: 2005 jun
Decide if additional Design Study needed | bar: 2005 may
Possible addendum to Design Study | Possible addendum to Design Study | bar: 2005 may to 2005 aug
Meeting of Network Target and Collector Sections | bar: 2005 sep
Minutes of Target & Collector Sections | bar: 2005 oct
Publish Proceedings of 1st International Conference on Targets and Collectors | Proc. 1st Int. Conf. on Targets & Collectors | bar: 2005 jan to 2005 nov
Meeting of Network Target and Collector Sections | bar: 2006 jan
Minutes of Target & Collector Sections | bar: 2006 feb
Attend NuFact06 | bar: 2006 apr
Meeting of Network Target and Collector Sections | bar: 2006 may
Minutes of Target & Collector Sections | bar: 2006 jun
Report on a specific SuperBeam solutions | Report on SuperBeam solutions | bar: 2006 jun to 2006 oct
2nd International Conference on Targets and Collectors | bar: 2005 nov to 2007 jan
Attend NuFact07 | bar: 2007 apr
Meeting of Network Target and Collector Sections | bar: 2007 may
Minutes of Target & Collector Sections | bar: 2007 jun
Meeting of Network Target and Collector Sections | bar: 2007 sep
Minutes of Target & Collector Sections | bar: 2007 oct
Publish Proceedings of 2nd International Conference on Targets and Collectors | Proc. 2nd Int. Conf. on Targets & Collectors | bar: 2007 jan to 2007 nov
Report on specific NuFact solutions | Report on specific NuFact solutions | bar: 2007 dec
Meeting of Network Target and Collector Sections. Define chapters for final report | bar: 2008 jan
Minutes of Target & Collector Sections | bar: 2008 feb
Attend NuFact07 | bar: 2008 apr
Meeting of Network Target and Collector Sections | bar: 2008 may
Minutes of Target & Collector Sections | bar: 2008 jun
Meeting of Network Target and Collector Sections | bar: 2008 sep
Minutes of Target & Collector Sections | bar: 2008 oct
Final Report | Final Report | bar: 2007 nov to 2008 nov
Table 1.2d-COLLECTOR WP4
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
| Initiate Web Site creation |  | web pages | bar: 2003 apr
| R&D project proposal (Design Studies) |  | Proposal | bar: 2003 apr to 2003 oct
| review simulation software |  | software repository | bar: 2003 jul
COLLECTOR WP4 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
Initiate Web Site creation | bar: 2003 apr
ENG Target and Collector Section Meeting | bar: 2003 apr
review present horn studies | bar: 2003 apr
Check particle collection simulation software | bar: 2003 apr
Propose horn material study | bar: 2003 may
Propose mechanical/thermal and power supply studies
Propose to define a road map on experimental program | bar: 2003 jul
Initiate horn test area study | bar: 2003 aug
Make status report on power supply design | bar: 2003 sep
Make status report on mechanical/thermal study | bar: 2003 oct
Propose compatibility checking with TARGET program | bar: 2003 nov
Initiate a proposal for new Horn prototype construction
integrated with the TARGET station (CTA)
First meeting of Network Target and Collector Sections.
Meeting of Target and Collector Sections | bar: 2004 mar
Make status report on CERN horn prototype | bar: 2004 apr
Initiate report on thermal diffusion coefficient measurements | bar: 2004 may
Review existing collection systems/new prototype first design | bar: 2004 jun
Meeting of Target and Collector Sections | bar: 2004 jul
Collector state of the art report | bar: 2004 aug
Review of test area requirements/status report power supply | bar: 2004 sep
Review CTA proposal | bar: 2004 oct
1st International Conference on Targets and Collectors | bar: 2005 mar
Review results on stress resistence limit of materials | bar: 2005 apr
Review final design of the new prototype | bar: 2005 jun
Make decision on additional TPW if needed
Review life time study of a 50 Hz horn | bar: 2005 aug
decide if additional TPW needed | bar: 2005 aug
addendum to CTA Proposal? | bar: 2005 sep
addendum to TTA Proposal? | bar: 2005 oct
Meeting of Network Target and Collector Sections | bar: 2005 nov
Meeting of Network Target and Collector Sections | bar: 2006 mar
Report on a specific SuperBeam solutions | bar: 2006 dec
2nd International Conference on Targets and Collectors | bar: 2007 mar
Laboratory Visits by Section Cordinator | bar: 2007 jun
Attend NuFact07 | bar: 2007 jul
Meeting of Network Target and Collector Sections | bar: 2007 nov
Report on specific NuFact solutions | bar: 2008 feb
Meeting of Target & Collector Sections. Define chapters for final report | bar: 2008 mar
Meeting of Network Target and Collector Sections | bar: 2008 nov
COLLECTOR WP4 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks (Join Target & Collector meeting) |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
Official Creation of the Europeen Network | bar: 2004 jan
| Make status report on power supply design |  | status report | bar: 2004 mar; 2005 mar; 2006 mar; 2007 mar; 2008 feb
| Make status report on irradiated material properties |  | status report | bar: 2004 mar; 2005 mar; 2006 mar; 2007 mar; 2008 feb
| Make status report on mechanical/thermal studies |  | status report | bar: 2004 mar; 2005 mar; 2006 mar; 2007 mar; 2008 feb
| Collector Test Area (CTA) proposal |  | Proposal | bar: 2003 nov to 2004 oct
| 1st International Conference on Targets and Collectors |  | participation & presentations, slides on www | bar: 2005 mar
| Publish Proceedings of 1st International Conference on Targets and Collectors |  | Proc. 1st Int. Conf. on Targets & Collectors | bar: 2005 mar to 2006 jan
Decide if additional Design Study needed | bar: 2005 jul
| Possible addendum to Design Study |  | Possible addendum to Design Study | bar: 2005 jul to 2005 oct
| Status Repport on CTA |  | Report | bar: 2004 nov to 2005 oct
| Report on specific SuperBeam solutions |  | Report | bar: 2005 oct to 2006 dec
| 2nd International Conference on Targets and Collectors |  | participation & presentations, slides on www | bar: 2007 mar
| Publish Proceedings of 2nd International Conference on Targets and Collectors |  | Proc. 2nd Int. Conf. on Targets & Collectors | bar: 2007 mar to 2008 jan
| Report on specific NuFact solutions |  | Report | bar: 2008 feb
| Final Report |  | Report | bar: 2008 jan to 2008 dec
| Initiate Web Site creation |  | web pages | bar: 2003 apr
| preparation of Proposal of Design Studies (DS) and R&D projects |  | Proposal Oct 03 | bar: 2003 apr to 2003 oct
| ENG Target and Collector Section Meeting |  | participation & presentations, slides on www | bar: 2003 apr
| review present horn studies |  | presentation | bar: 2003 apr
| Check particle collection simulation software |  | software repository
| Propose horn material study |  | presentations | bar: 2003 apr to 2005 sep
| Propose mechanical/thermal and power supply studies |  | presentation | bar: 2003 apr to 2005 sep
| Propose to define a road map on experimental program |  | presentation | bar: 2003 apr to 2003 oct
| Make status report on power supply design |  | document? | bar: 2003 jul
| Make status report on mechanical/thermal study |  | document? | bar: 2003 jul
| Make status report on CERN horn prototype |  | document? | bar: 2003 jul
| Make Status report on cooling system |  | document? | bar: 2003 sep
| preparation of Collector Test Area proposal |  | Proposal Oct 04 | bar: 2003 nov to 2005 jun
| Meeting of Target and Collector Sections |  | participation & presentations, slides on www | bar: 2004 mar
| Attend NuFact04 |  | participation & presentations, slides on www | bar: 2004 jun
| Meeting of Network Target and Collector Sections |  | participation & presentations, slides on www | bar: 2004 jul
| Make status report on power supply design |  | document? | bar: 2004 sep
| Make status report on mechanical/thermal study |  | document? | bar: 2004 sep
| Review of test area requirements |  | document? | bar: 2004 sep
| 1st International Conference on Targets and Collectors |  | participation & presentations, slides on www | bar: 2005 mar
Review results on stress resistence limit of materials | bar: 2005 apr
| Attend NuFact05 |  | participation & presentations, slides on www | bar: 2005 jun
Make decision on additional TPW if needed
Review life time study of a 50 Hz horn | bar: 2005 aug
decide if additional TPW needed | bar: 2005 aug
possible addendum to CTA Proposal | bar: 2005 jun to 2005 sep
| Meeting of Network Target and Collector Sections |  | participation & presentations, slides on www | bar: 2005 nov
| Meeting of Network Target and Collector Sections |  | participation & presentations, slides on www | bar: 2006 apr
| Attend NuFact06 |  | participation & presentations, slides on www | bar: 2006 jun
| Report on a specific SuperBeam solutions |  | document? | bar: 2006 dec
| 2nd International Conference on Targets and Collectors |  | participation & presentations, slides on www | bar: 2007 mar
| Attend NuFact07 |  | participation & presentations, slides on www | bar: 2007 jul
| Meeting of Network Target and Collector Sections |  | participation & presentations, slides on www | bar: 2007 nov
| Report on specific NuFact solutions |  | document? | bar: 2008 feb
| Meeting of Target & Collector Sections. Define chapters for final report |  | participation & presentations, slides on www | bar: 2008 mar
| Meeting of Network Target and Collector Sections |  | participation & presentations, slides on www | bar: 2008 nov
Table 1.2e-MUFRONT WP5
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
| Formation of expanded EU network |  | Team to work on NuFact design | bar: 2003 apr
| First review of existing NuFact designs |  | Initial report on existing NuFact designs | bar: 2003 apr
Start learning phase for new people | bar: 2003 apr
Initiate detailed study of MICE systematics | bar: 2003 apr
| Complete detailed network work plan |  | Network work plan | bar: 2003 oct
MUFRONT WP5 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
Start review of European, US and Japanese designs | bar: 2004 mar
Initiate comparison of alternative designs | bar: 2004 may
| Produce report on MICE systematic error studies |  | Report on MICE systematic errors | bar: 2004 jul
| Detailed review of existing designs |  | Detailed report on existing designs | bar: 2004 nov
| Complete review of US/Japan alternatives |  | Report on US/Japanese designs | bar: 2005 jan
| Workshop: detailed comparison of frontends |  | Minutes of comparison workshop | bar: 2005 mar
| Review of designs with other components |  | Report on first overall design review | bar: 2005 may
Determine R&D and other work required to | bar: 2005 jun
select optimum design
| Write R&D proposals and start fundraising |  | R&D proposals | bar: 2005 jul
select & cost accelerating option | bar: 2005 sep
Assess MICE usefulness for alternative frontends | bar: 2005 oct
| Propose MICE experiments for alternative FEs |  | Proposal for alternative MICE expts | bar: 2006 may
| Workshop: preliminary R&D results |  | Minutes of R&D workshop | bar: 2007 jan
First observation of cooling In MICE | bar: 2007 mar
| Assessment of first MICE results |  | Report on first MICE results | bar: 2007 apr
| Workshop: overall optimisation of NF design |  | Minutes of optimisation workshop | bar: 2007 jul
| Detailed assessment of MICE results |  | Detailed report on MICE results | bar: 2007 sep
| Workshop: select optimal NuFact design |  | Report on optimal NuFact design | bar: 2008 jan
Define chapter for final report | bar: 2008 mar
| present draft of final chapter |  | CDR chapter | bar: 2008 jun
Table 1.2f-MUEND WP6
Task |  |  | deliverable | 2003 apr: 2003; 2004 jan: 2004; 2005 jan: 2005; 2006 jan: 2006; 2007 jan: 2007; 2008 jan: 2008; 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
ECFA Muon Week |  |  | participations & presentations, slides on www | bar: 2003 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | contributions to Workshop and Proceedings | bar: 2003 jun
preparation of Proposal of Design Studies (DS) and R&D projects |  |  | Proposal Oct 03 | bar: 2003 apr to 2003 oct
CARE and BENE founding meeting at CERN |  |  | participations & presentations, slides on www | bar: 2003 nov
MUEND WP6 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
| launch working group activities |  | chart of work organization | bar: 2004 feb to 2004 mar
| participation to NuFact04 Workshop |  | Workshop Proceedings | bar: 2004 feb to 2004 jun
| RLA vs FFAG : define terms of comparative study |  | chart of terms of comparison | bar: 2004 apr to 2004 oct
| participation to yearly FFAG Workshop |  | Workshop Proceedings | bar: 2004 may to 2004 sep
| first proposal of R&D plans, RF cavities and magnets |  | R&D plan | bar: 2004 nov
| participation to NuFact05 Workshop |  | Workshop Proceedings | bar: 2005 feb to 2005 jun
| participation to yearly FFAG Workshop |  | Workshop Proceedings | bar: 2005 may to 2005 sep
| status of RLA/FFAG comparison |  | report on RLA/FFAG comparison | bar: 2005 sep to 2005 oct
| status of the studies on RF cavities and magnets |  | revised R&D plan | bar: 2005 nov
| participation to NuFact06 Workshop |  | Workshop Proceedings | bar: 2006 feb to 2006 jun
| participation to yearly FFAG Workshop |  | Workshop Proceedings | bar: 2006 may to 2006 sep
| revision of status of RLA/FFAG comparison |  | rievised report on RLA/FFAG comparison | bar: 2006 sep to 2006 oct
| revision of status of studies on RF cavities and magnets |  | revised R&D plan | bar: 2006 nov
| participation to NuFact07 Workshop |  | Workshop Proceedings | bar: 2007 feb to 2007 jun
| participation to yearly FFAG Workshop |  | Workshop Proceedings | bar: 2007 may to 2007 sep
| revision of status of RLA/FFAG comparison |  | rievised report on RLA/FFAG comparison | bar: 2007 sep to 2007 oct
| revision of status of studies on RF cavities and magnets |  | revised R&D plan | bar: 2007 nov
| review of Europe, Japan and US RLA/FFAG studies & experiments |  | report & recommendations | bar: 2007 dec to 2008 mar
| prepare draft of chapter Acceleration & Storage design |  | draft of chapter of final report | bar: 2008 jan to 2008 jul
| participation to NuFact08 Workshop |  | Workshop Proceedings | 2009 jan: 2009
| participation to yearly FFAG Workshop |  | Workshop Proceedings | [69 empty] | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
| finalize chapter on Acceleration & Storage design |  | chapter of final report
Table 1.2g-BETABEAM WP7
Task |  |  | deliverable | 2003 | [8 empty] | 2004 | [11 empty] | 2005 | [11 empty] | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009 jan: 2009
|  |  |  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
pre BENE Timetable |  |  | deliverable
Moriond Workshop |  |  | All presentations on web site | bar: 2003 apr
Evaluation of base line scenario |  |  | Presentation and paper at 1st meeting | bar: 2003 apr to 2003 oct
Evaluation of physics case (including low energy neutrinos) |  |  | Presentation and report for Nufact | bar: 2003 apr to 2003 dec
1st Betabeam meeting (GSI?) |  |  | Proceedings on the web | bar: 2003 nov
BETABEAM WP7 Timetable |  |  | deliverable | bar: 2004 jan to 2008 dec
ECFA Muon Weeks |  |  | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact International Workshop on Neutrino Factory & Superbeam |  |  | participation & contributions to Workshop | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE (& BENE) Week |  |  | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
| Evaluation of physics case (including low energy neutrinos) |  | Presentation and report for Nufact | bar: 2004 jan to 2005 apr
| Evaluation of tests of stacking schemes in existing accelerators |  | Presentation and report for 2nd WS | bar: 2003 nov to 2004 oct
| Evaluation of limits for the betabeam of stripping accumulation in existing accelerators |  | Presentation and report for 2nd WS | bar: 2003 nov to 2004 oct
| Evaluation of tests of target prototypes at existing facilities |  | Presentation and report for Nufact | bar: 2003 nov; 2004 apr to 2005 apr
| Evaluation of design work on new machines for the beta-beam |  | Presentation and report for Nufact | bar: 2003 oct to 2005 apr
| Evaluation of "exotic" alternatives for isotope production |  | Presentation and report for 2nd WS | bar: 2003 oct to 2004 oct
| Evaluation of ion source alternatives |  | Presentation and report for 2nd WS | bar: 2003 oct to 2004 oct
| Evaluation of activation in decay ring |  | Presentation and report for Nufact | bar: 2003 jul to 2005 apr
| Evalution of civil engineering requirements |  | Presentation and report for 2nd WS | bar: 2003 sep to 2004 oct
| Second beta-beam workshop |  | Proceedings on the web | bar: 2004 mar
| Evaluation of on-going work for the beta-beam |  | Presentations and reports | bar: 2005 jun to 2009 oct
| 2nd Beta-beam meeting |  | Proceedings on the web | bar: 2004 nov
| NuFACT 05 in Europe |  | Procedings | bar: 2005 may
Publication of intermediate report | bar: 2005 jun
| 3rd Beta-beam meeting |  | Proceedings on the web | bar: 2005 nov
| 3rd beta-beam workshop |  | Proceedings on the web | bar: 2006 mar
| 4th Beta-beam meeting |  | Proceedings on the web | bar: 2006 nov
| 4th beta-beam workshop |  | Proceedings on the web | bar: 2007 feb
| 5th Beta-beam meeting |  | Proceedings on the web | bar: 2007 nov
| Nufact 08 |  | Proceedings on the web | bar: 2008 jun
| 6th Beta-beam meeting |  | Proceedings on the web | bar: 2008 mar
Define chapter for final report | bar: 2008 mar
| present draft of final chapter |  | Draft of final report | bar: 2008 jun