## Sheet1
activity | deliverable | 2003 | [8 empty] | 2004 | [11 empty] | 2005 | [11 empty] | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009
|  | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
BENE Week | meeting, slides on www | bar: 2003 jul
NuFact & Superbeam Int. Workshop | contributions to Proceedings | bar: 2003 jun
preparation of Proposal of Design Studies (DS) and R&D projects | Proposal Oct 03 | bar: 2003 apr to 2003 oct
CARE and BENE founding meeting at CERN | meeting, slides on www | bar: 2003 nov
BENE Timetable | deliverable | bar: 2004 jan to 2008 dec
BENE Week | participation & presentations, slides on www | bar: 2004 mar; 2004 jul; 2005 mar; 2005 jul; 2006 mar; 2006 jul; 2007 mar; 2007 jul; 2008 mar; 2008 jul; 2009 mar; 2009 jul
NuFact04 & Superbeam Int. Workshop | participation to Workshop in Japan | bar: 2004 jun; 2005 jun; 2006 jun; 2007 jun; 2008 jun; 2009 jun
CARE and BENE Week | participation & presentations, slides on www | bar: 2004 nov; 2005 nov; 2006 nov; 2007 nov; 2008 nov
preparation of contributions to NuFact04 Workshop | contributions to Workshop | bar: 2004 mar to 2004 jun
preparation of writeups for NuFact Proceedings | contributions to Proceeedings | bar: 2004 jul to 2004 sep
preparation of Proposal of additional R&D projects | Proposal Oct 04 | bar: 2004 apr to 2004 oct
preparation of additional JRP proposals (if any) | Proposals Apr 05? | bar: 2004 nov to 2005 mar
preparation of Interim Report (end of first comparative studies) | Interim Report Jun 05 | bar: 2004 dec to 2005 jun
( road map towards CDR's + first set of firm parameters) | bar: 2004 dec to 2005 jun
preparation of NuFact05 & Superbeam Int. Workshop | organization of Workshop in Europe | bar: 2005 jan to 2005 jun
preparation of contributions to NuFact Workshop | contributions to Workshop | bar: 2005 mar to 2005 jun
preparation of writeups for NuFact05 Proceedings | contributions to Proceeedings | bar: 2005 jul to 2005 sep
preparation of Proposal of additional R&D projects | Proposal Oct 05 | bar: 2005 apr to 2005 oct
editing and publication of NuFact05 Proceedings | Proceedings end 05 | bar: 2005 oct to 2005 nov
preparation of final general and WP reports | Final Report Dec 08 | bar: 2005 jul to 2008 dec
( status and road map to TDR) | bar: 2005 jul to 2008 dec
preparation of NuFact08 & Superbeam Int. Workshop | organization of Workshop in Europe | bar: 2008 jan to 2008 jun
draft final general and WP reports | draft of final report Jun 05 | bar: 2008 feb to 2008 jun
preparation of writeups for NuFact08 Proceedings | contributions to Proceeedings | bar: 2008 jul to 2008 sep
editing and publication preparation of NuFact08 Proceedings | Proceedings end 08 | bar: 2008 oct to 2008 nov
completion of final general and WP reports | Final "Road Map" Report Dec 08 | bar: 2008 jul to 2008 dec
PHYSICS WP1 Timetable | deliverable | bar: 2004 jan to 2008 dec
PHYSICS
"Munich Workshop" on Ambiguities, Degeneracies and Correlations in the search for Leptonic CP, possible exp. strategies (Munich?) | organization of Workshop | bar: 2004 dec
"Munich report" on the same subject | Proceedings | bar: 2005 jun
preparation of interim (preliminary road map) report | Interim Report Jun 05 | bar: 2005 jun
"Valencia Workshop" on SuperBeams vs. Beta Beams vs NuFact, synergies and priorities (Valencia ?) | organization of Workshop | bar: 2006 feb
"Valencia report" on the same subject | Proceedings | bar: 2006 sep
intermediate report
preliminary road map
"Valencia Workshop" on SuperBeams vs. Beta Beams vs NuFact, synergies and priorities (Valencia ?)
"Valencia report" on the same subject
A report on an optimized parameter list for SB, BB and NF. Addressing the problems of systematic errors | Report | bar: 2007 sep
Define chapter for final report | Report Layout | bar: 2008 mar
A report on an optimized parameter list for SB, BB and NF. Addressing the problems of systematic errors
present draft of BENE final report | Draft Final Report Jun 08 | bar: 2008 jun
final "roadmap report" | Final Report Dec 08 | bar: 2008 dec
DRIVER WP2 Timetable | deliverable | bar: 2004 jan to 2008 dec
launch full comparative study | bar: 2004 jan
assess HARP data | bar: 2004 jul
review HIPPI status report | bar: 2004 nov
proton source tests, chopper study
tests of RF bunchers
SPL vs RCS: define comparative study
review HIPPI progress report | bar: 2005 mar
accelerating structure 1,
elliptical cavity
SPL vs RCS: preliminary conclusions
review HIPPI progress report | bar: 2005 jul
first RFQ tests, chopper design
beam transport
ECR source modelisation
results of the studies for most elements | bar: 2005 dec
Driver Workshop | bar: 2006 jul
revision of the R&D plans | bar: 2006 dec
Driver Workshop | bar: 2007 jul
revision of the R&D plans | bar: 2007 dec
present draft of final chapter | bar: 2008 jun
Driver Workshop | bar: 2008 jul
final report, driver TDR | bar: 2008 dec
TARGET WP3 Timetable | deliverable | bar: 2004 jan to 2008 dec
identify nature, location & first list of experiments for a Target Test Area (TTA) | bar: 2003 apr
start TTA design, prepare proposal | bar: 2003 jun
Proposal TTA | bar: 2003 oct
First meeting of Network Target and Collector Sections. | bar: 2003 nov
Laboratory Visits by Section Cordinator | bar: 2004 jan
Meeting of Target and Collector Sections | bar: 2004 mar
Laboratory Visits by Section Cordinator | bar: 2004 may
Attend NuFact04 | bar: 2004 jun
Meeting of Target and Collector Sections | bar: 2004 jul
1st International Conference on Targets and Collectors | bar: 2005 mar
Laboratory Visits by Section Cordinator | bar: 2005 may
Attend NuFact05 | bar: 2005 jun
decide if additional TPW needed | bar: 2005 aug
addendum to TTA Proposal? | bar: 2005 oct
Meeting of Network Target and Collector Sections | bar: 2005 nov
Meeting of Network Target and Collector Sections | bar: 2006 mar
Laboratory Visits by Section Cordinator | bar: 2006 may
Attend NuFact06 | bar: 2006 jun
Report on a specific SuperBeam solutions | bar: 2006 dec
2nd International Conference on Targets and Collectors | bar: 2007 mar
Laboratory Visits by Section Cordinator | bar: 2007 may
Attend NuFact07 | bar: 2007 jun
Meeting of Network Target and Collector Sections | bar: 2007 nov
Report on specific NuFact solutions | bar: 2008 feb
Meeting of Target and Collector Sections. Define chapters for final report | bar: 2008 mar
Laboratory Visits by Section Cordinator | bar: 2008 may
Attend NuFact07
Meeting of Network Target and Collector Sections | bar: 2008 nov
COLLECTOR WP4 Timetable | deliverable | bar: 2004 jan to 2008 dec
Initiate Web Site creation | web pages | bar: 2003 apr
R&D project proposal (Design Studies) | Proposal Oct 03 | bar: 2003 apr to 2003 oct
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2003 apr
review simulation software | software repository | bar: 2003 jul
Official Creation of the Europeen Network | bar: 2004 jan
Collector Test Area (CTA) proposal | Proposal Oct 04 | bar: 2003 nov to 2004 oct
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2004 mar
Attend NuFact04 | participation & presentations, slides on www | bar: 2004 jun
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2004 jul
1st International Conference on Targets and Collectors | participation & presentations, slides on www | bar: 2005 mar
Attend NuFact05 | participation & presentations, slides on www | bar: 2005 jun
Status Repport on CTA | bar: 2004 nov to 2005 sep
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2005 nov
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2006 apr
Attend NuFact06 | participation & presentations, slides on www | bar: 2006 jun
Report of First Design of an Integrated Target and Collector | Report Nov06 | bar: 2005 oct to 2006 nov
2nd International Conference on Targets and Collectors | participation & presentations, slides on www | bar: 2007 mar
Attend NuFact07 | participation & presentations, slides on www | bar: 2007 jul
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2007 nov
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2007 nov
Chapters for final report | Report Mars08 | bar: 2007 aug to 2008 mar
Target and Collector Sections Meeting | participation & presentations, slides on www | bar: 2008 nov
NUFACT WP5 Timetable | deliverable | bar: 2004 jan to 2008 dec
Formation of expanded EU network | bar: 2003 apr
First review of existing NuFact designs | bar: 2003 apr
Start learning phase for new people | bar: 2003 apr
Initiate detailed study of MICE systematics | bar: 2003 apr
Complete detailed network work plan | bar: 2003 oct
Start review of US and Japanese designs | bar: 2004 mar
Initiate studies of alternative designs | bar: 2004 may
Produce report on MICE systematic error studies | bar: 2004 jul
review recirculating linacs and FFAG | bar: 2004 aug
Detailed review of existing designs | bar: 2004 nov
Complete review of US/Japan alternatives | bar: 2005 jan
Workshop: detailed comparison of frontends | bar: 2005 mar
Review of designs with other components | bar: 2005 may
Determine R&D and other work required to | bar: 2005 jun
select optimum design
Write R&D proposals and start fundraising | bar: 2005 jul
select & cost accelerating option | bar: 2005 sep
Assess MICE usefulness for alternative frontends | bar: 2005 oct
Propose MICE experiments for alternative FEs | bar: 2006 may
Workshop: preliminary R&D results | bar: 2007 jan
First observation of cooling In MICE | bar: 2007 mar
Assessment of first MICE results | bar: 2007 apr
Workshop: overall optimisation of NF design | bar: 2007 jul
Detailed assessment of MICE results | bar: 2007 sep
Workshop: select optimal NuFact design | bar: 2008 jan
Define chapter for final report | bar: 2008 mar
present draft of final chapter | bar: 2008 jun
BETABEAM WP6 Timetable | deliverable | bar: 2004 jan to 2008 dec
Moriond Workshop | bar: 2003 apr
Moriond follow up in GSI | bar: 2003 sep
Workshop II in Legnaro? | bar: 2004 mar
Int. Workshop on betabeams | bar: 2004 may
Publication of intermediate report | bar: 2005 jun
Define chapter for final report | bar: 2008 mar
present draft of final chapter | bar: 2008 jun