## Sheet1
|  |  | Events | BENE NA | PHYSICS | DRIVER | TARGET | COLLECTOR | m FRONTEND | m ACCELERATION | BETABEAM | DS NuFact | DS Betabeam
2003 | Feb |  |  | 2nd presentation to MUG | [7 empty] | 1st presentation to MUG | 1st presentation to MUG
2003 | Feb-Mar | [10 empty] | definition with RAL of names & ways
2003 | Mar | 18 to 22 | [8 empty] | Moriond Workshop |  | Moriond Workshop
2003 | Mar | 24 to 28 | Muon Week CERN | 2nd presentation to MCOG |  |  |  |  | intensify MICE fundraising |  |  | 1st presentation to MCOG | 1st presentation to MCOG
2003 | Mar | 29 | ECFA | final approval by ECFA | [7 empty] | 1st presentation to ECFA | 1st presentation to ECFA
2003 | Apr |  |  | submission |  |  | identify nature, location & first | Collector Test Area : costing & | plan R&D on RF power sources |  |  | define key points to be studied
[7 empty] | list of experiments | experimental programme | plan R&D large fast kickers
2003 | May | [5 empty] | for a Target Test Area | prepare proposal | plan R&D on acceleration |  |  | & work program
2003 | Jun | 5 to 11 | NuFact03 New York |  |  |  | start TTA design, prepare proposal |  | prepare proposal
2003 | Jul | 7 to 11 | Muon Week CERN | approval? | [5 empty] | design work on recirculating linacs and FFAG
2003 | Aug | [5 empty] | identify final >4MW target design team
2003 | Sep | [9 empty] | Moriond follow up in GSI
2003 | Oct | [5 empty] | Proposal TTA | CTA Proposal | Proposal global R&D program |  |  | submission (FS(+) & 1st batch of TPW(°)) | submission
2003 | Nov | 2003-11-07 | NIB03(*), KEK
2003 | Nov | 17-21 | Muon Week CERN
2003 | Dec | [10 empty] | approval?
2004 | Jan | 1 |  | funding begins |  | launch full comparative study
2004 | Feb | [5 empty] | First meeting of Target with Collector
2004 | Mar |  | Muon Week (Legnaro?) | final definition of 2nd batch of TPW proposals |  |  | start construction of solenoid | start horn construction | European network formed and working |  | Workshop II in Legnaro? |  | Moriond Workshop II in Legnaro?
2004 | Apr | [6 empty] | design power supply
2004 | May | [6 empty] | make other orders | comaprison with cooling free approaches
2004 | Jun |  | NuFact04 Japan | [5 empty] | analysis of MICE systematics |  | Int. Workshop on betabeams
2004 | Jul |  | Muon Week |  |  | assess HARP data | First Main meeting of Target and Collector |  |  | design work on recirculating linacs and FFAG |  | funding begins | funding begins
2004 | Aug | [6 empty] | Collector state of the art report
2004 | Sep | [7 empty] | first analysis of ring cooling
2004 | Oct | [10 empty] | submission of more TPW activities? | submission of more TPW activities?
2004 | Nov |  | Muon Week | final definition of JRP proposals, if any |  |  |  | start horn characterization | MICE beam characterization
2004 | Dec |  |  |  | "Munich Workshop" on Ambiguities, Degeneracies and Correlations in the search for Leptonic CP, possible exp. strategies (Munich?) | state of the art & R&D strategy report | State of the art report target and collector |  | realistic fields in baseline simulations
2005 | Jan | [5 empty] | Preliminary recommendations for R&D.
2005 | Feb | [5 empty] | solenoid or/and beam together
2005 | Mar |  | Muon Week | final definition of 3rd batch of TPW proposals
2005 | Apr |  |  | submission of more CARE JRP's(^)? |  |  | test of granulated target
2005 | May |  |  |  | "Munich report" on the same subject |  |  |  | start build kicker
2005 | Jun |  | NuFact05 Europe | end of comparative studies | intermediate report | choose SPL vs RCS | start design of final >4MW target | start design of final collection | assess baseline cooler performance | select & cost accelerating option | Publication of intermediate report
|  |  |  | road map to CDRs, 1st sets of parameters etc | preliminary road map | start final driver design | decide if additional TPW needed | decide if additional TPW needed
2005 | Jul |  | Muon Week |  |  |  | 1st International Conference on Targets and Collectors
2005 | Aug
2005 | Sep | [6 empty] | life time study of a 50 Hz horn | preliminary ring cooler design
2005 | Oct | [5 empty] | addendum to TTA Proposal? | addendum to CTA Proposal? | assess MICE usefulness for alternative frontends |  |  | submission of more TPW activities? | submission of more TPW activities?
2005 | Nov |  | Muon Week | [5 empty] | first emittances measurement in MICE
2005 | Dec |  |  |  |  | results of the studies for most elements |  |  | first NuFact frontend optimizations
2006 | Jan | [5 empty] | Publication of Conference Proceedings
2006 | Feb |  |  |  | "Valencia Workshop" on SuperBeams vs. Beta Beams vs NuFact, synergies and priorities (Valencia ?) |  | test of granulated target+horn
2006 | Mar |  | Muon Week
2006 | Apr
2006 | May
2006 | Jun |  | NuFact06 USA | [5 empty] | prepare NuFact frontend R&D
2006 | Jul |  | Muon Week |  |  |  | 2nd Main meeting of the Target and Collector Sections. |  | bring kicker to completion
2006 | Aug | [5 empty] | observe beam in jet & solenoid
2006 | Sep |  |  |  | "Valencia report" on the same subject
2006 | Oct | [5 empty] | interim report on Target and Collector developments.
2006 | Nov |  | Muon Week |  |  |  | Recommendations for future R&D.
2006 | Dec |  |  |  |  | revision of the R&D plans |  | Report on a specific SuperBeam solutions
2007 | Jan
2007 | Feb
2007 | Mar |  | Muon Week | [5 empty] | first observation of cooling In MICE
2007 | Apr | [7 empty] | assess MICE first results
2007 | May
2007 | Jun |  | NuFact07 Japan
2007 | Jul |  | Muon Week |  |  |  | 2nd International Conference on Targets and Collectors |  | test kicker in text beam
2007 | Aug
2007 | Sep |  |  |  | A report on an optimized parameter list for SB, BB and NF. Addressing the problems of systematic errors |  |  |  | define & propose MICE additional measurements
2007 | Oct
2007 | Nov |  | Muon Week | [5 empty] | complete NuFact frontend optimizations
2007 | Dec |  |  |  |  | revision of the R&D plans |  |  | further MICE experiments
2008 | Jan | [5 empty] | Publication of Conference Proceedings
2008 | Feb | [6 empty] | Report on specific NuFact solutions
2008 | Mar |  | Muon Week | discuss final draft of CDR | chapter for CDR | chapter for CDR | chapter for CDR | chapter for CDR | chapter for CDR |  | chapter for CDR
2008 | Apr
2008 | May | [7 empty] | assess impact of full MICE results
2008 | Jun |  | NuFact08 Europe | present NuFact Conceptual Design Report
2008 | Jul |  | Muon Week |  |  |  | 3rd Main and final meeting of the Target and Collector Sections
2008 | Aug
2008 | Sep | [7 empty] | complete comparison of frontends
2008 | Oct
2008 | Nov |  | Muon Week
2008 | Dec |  |  | end of NA: final reports and general report | final "roadmap report" | final report, driver TDR | Final report and recommendations of the Target and Collector Sections |  | final report with additional R&D program
road map to future
2009 | Jan
2009 | Feb
2009 | Mar |  | Muon Week
2009 | Apr
2009 | May
2009 | Jun | [10 empty] | end of DS, after 1 year of consolidation | end of DS
& maybe work towards a TDR
|  | * | Neutrino Beam Instrumentation Workshop, rotates yearly
|  | + | Feasibility Study (paperwork)
|  | ° | Technical Preparatory Work (R&D)
|  | ^ | Joint Research Project. Must be worded in terms of improvements of existing facilities
[6 empty] | Spring 2004 | Initial meeting of the Target and Collector Sections. Allotment of specific duties.
[6 empty] | Summer 2004 | 1st Main Meeting (with international participants) to present the current progress in target and collector studies.
[6 empty] | Winter 2004 | Publication of the current position of target and collector development.
Preliminary recommendations for future R&D.
[6 empty] | Summer 2005 |  | 1st International Conference on Targets and Collectors.
[6 empty] | Spring 2006 |  | Publication of Conference Proceedings.
[6 empty] | /Summer |  | 2nd Main meeting of the Target and Collector Sections.
[6 empty] | Autumn 2006 | Publication of interim report on Target and Collector developments.
Recommendations for future R&D.
[6 empty] | Summer 2007 |  | 2nd International Conference on Targets and Collectors.
[6 empty] | Spring 2008 |  | Publication of Conference Proceedings.
[6 empty] | /Summer | 3rd Main and final meeting of the Target and Collector Sections.
[6 empty] | Winter 2008 | Final report and recommendations of the Target and Collector Sections