## Sheet1
|  |  | Events | BENE NA | PHYSICS | DRIVER | TARGET | COLLECTOR | COLLECTOR Roger/mine | TARGET Roger | COLLECTOR Roger | TARGET Jean Eric | COLLECTOR Jean Eric | TARGET | COLLECTOR | TARGET | COLLECTOR | NuFact | BETABEAM | DS NuFact | DS Betabeam | NuFact | m ACCELERATION
2003 | Feb |  |  | 2nd presentation to MUG | [15 empty] | 1st presentation to MUG | 1st presentation to MUG
2003 | Feb-Mar | [11 empty] | Initiate Web Site creation | [6 empty] | definition with RAL of names & ways
2003 | Mar | 18 to 22 | [5 empty] | Initiate Web Site creation |  |  |  | review tagert studies | review present horn studies |  |  |  | Initiate Web Site creation |  | Moriond Workshop |  | Moriond Workshop
2003 | Mar | 24 to 28 | BENE Week CERN | 2nd presentation to MCOG |  |  |  | review present horn studies |  |  |  |  | Check particle collection simulation software |  |  | ENG Target and Collector Section Meeting | review present horn studies | Formation of expanded EU network |  | 1st presentation to MCOG | 1st presentation to MCOG | Formation of expanded EU network
2003 | Mar | 29 | ECFA | final approval by ECFA | [8 empty] | Propose horn material study |  |  |  |  | First review of existing NuFact designs |  | 1st presentation to ECFA | 1st presentation to ECFA | First review of existing NuFact designs
2003 | Apr |  |  | submission |  |  | identify nature, location & first | Check particle collection simulation software | Collector Test Area : costing & | identify nature, location & first | Collector Test Area : costing & |  | Propose mechanical/thermal and power supply studies | identify nature, location & first | Collector Test Area : costing & | identify nature, location & first list of experiments for a Target Test Area | Check particle collection simulation software | Start learning phase for new people |  | define key points to be studied |  | Start learning phase for new people
[7 empty] | list of experiments |  | experimental programme | list of experiments | experimental programme | identify final 4MW target design team |  | list of experiments | experimental programme |  |  | Initiate detailed study of MICE systematics |  |  |  | Initiate detailed study of MICE systematics
2003 | May | [5 empty] | for a Target Test Area | Propose horn material study | prepare proposal | for a Target Test Area | prepare proposal | proposal for target test prototype | Propose to define a road map on experimental program | for a Target Test Area | prepare proposal |  | Propose horn material study |  |  | & work program
[8 empty] | Propose mechanical/thermal and power supply studies | [8 empty] | Propose mechanical/thermal and power supply studies
2003 | Jun | 5 to 11 | NuFact03 New York |  |  |  | start TTA design, prepare proposal |  |  | start TTA design, prepare proposal |  | start Target test area desing | Initiate horn test area study | start TTA design, prepare proposal |  | start TTA design, prepare proposal
2003 | Jul | 7 to 11 | BENE Week CERN | approval? |  |  |  | Propose to define a road map on experimental program |  |  |  |  | Make status report on power supply design |  |  |  | Propose to define a road map on experimental program | [5 empty] | design work on recirculating linacs and FFAG
2003 | Aug | [5 empty] | identify final >4MW target design team | Initiate horn test area study |  | identify final >4MW target design team |  |  | Make status report on mechanical/thermal study | identify final >4MW target design team |  |  | Initiate horn test area study
2003 | Sep | [6 empty] | Make status report on power supply design |  |  |  | check compatibility with collector exp. prog | Propose compatibility checking with TARGET program |  |  |  | Make status report on power supply design |  | Moriond follow up in GSI
2003 | Oct | [5 empty] | Proposal TTA | Make status report on mechanical/thermal study | CTA Proposal | Proposal TTA | CTA Proposal |  | Initiate a proposal for new Horn prototype construction | Proposal TTA | CTA Proposal | Proposal TTA | Make status report on mechanical/thermal study | Complete detailed network work plan |  | submission (FS(+) & 1st batch of TPW(°)) | submission | Complete detailed network work plan
2003 | Nov | 2003-11-07 | NIB03(*), KEK | CARE FOUNDING EVENT |  |  |  | Propose compatibility checking with TARGET program |  |  |  |  | integrated with the TARGET station (CTA) |  |  |  | Propose compatibility checking with TARGET program
[8 empty] | Initiate a proposal for new Horn prototype construction | [8 empty] | Initiate a proposal for new Horn prototype construction
2003 | Nov | 17-21 | BENE Week CERN | CARE FOUNDING MEETING at CERN |  |  |  | integrated with the TARGET station (CTA) |  |  |  | Draft Proposal TTA |  |  |  | First meeting of Network Target and Collector Sections. | integrated with the TARGET station (CTA)
2003 | Dec | [18 empty] | approval?
2004 | Jan | 1 |  | funding begins |  | launch full comparative study | First meeting of Target with Collector |  |  | First meeting of Target with Collector |  | First meeting of Target with Collector |  |  |  | Laboratory Visits by Section Cordinator
2004 | Feb | [10 empty] | start construction test targets |  | First meeting of Target with Collector
2004 | Mar |  | BENE Week (Legnaro?) | final definition of 2nd batch of TPW proposals |  |  |  |  | start horn construction |  | start horn construction | first proposal for target/horn integration | Make status report on CERN horn prototype | start construction of solenoid | start horn construction | Meeting of Target and Collector Sections |  | Start review of US and Japanese designs | Workshop II in Legnaro? |  | Moriond Workshop II in Legnaro? | Start review of US and Japanese designs
2004 | Apr | [6 empty] | Make status report on CERN horn prototype | design power supply |  | design power supply |  | Initiate report on thermal diffusion coefficient measurements |  | design power supply |  | Make status report on CERN horn prototype
2004 | May | [6 empty] | Initiate report on thermal diffusion coefficient measurements | make other orders |  | make other orders |  | Review existing collection systems/new prototype first design |  | make other orders | Laboratory Visits by Section Cordinator | Initiate report on thermal diffusion coefficient measurements | Initiate studies of alternative designs |  |  |  | Initiate studies of alternative designs
2004 | Jun |  | NuFact04 Japan |  |  |  |  | Review existing collection systems/new prototype first design |  |  |  | First Main meeting of Target and Collector |  |  |  | Attend NuFact04 | Review existing collection systems/new prototype first design |  | Int. Workshop on betabeams
2004 | Jul |  | BENE Week |  |  | assess HARP data | First Main meeting of Target and Collector |  |  | First Main meeting of Target and Collector |  |  | Collector state of the art report | First Main meeting of Target and Collector |  | Meeting of Target and Collector Sections |  | Produce report on MICE systematic error studies |  | funding begins | funding begins | Produce report on MICE systematic error studies | design work on recirculating linacs and FFAG
2004 | Aug | [6 empty] | Collector state of the art report | Collector state of the art report |  | Collector state of the art report |  | Review of test area requirements/status report power supply |  | Collector state of the art report |  | Collector state of the art report | review recirculating linacs and FFAG
2004 | Sep | [6 empty] | Review of test area requirements/status report power supply |  |  |  | TTA proposal | Review CTA proposal |  |  |  | Review of test area requirements/status report power supply
2004 | Oct | [6 empty] | Review CTA proposal | [8 empty] | Review CTA proposal |  |  | submission of more TPW activities? | submission of more TPW activities?
2004 | Nov |  | BENE & CARE Week | final definition of JRP proposals, if any |  | review HIPPI status report | State of the art report target and collector |  |  | State of the art report target and collector |  | State of the art report target and collector |  |  | start horn characterization |  |  | Detailed review of existing designs |  |  |  | Detailed review existing designs
2004 | Dec |  |  |  | "Munich Workshop" on Ambiguities, Degeneracies and Correlations in the search for Leptonic CP, possible exp. strategies (Munich?) | proton source tests, chopper study | Preliminary recommendations for R&D. |  |  | Preliminary recommendations for R&D. |  | Preliminary recommendations for R&D. |  | State of the art report target and collector
2005 | Jan |  |  |  |  | tests of RF bunchers | [5 empty] | test of granular target |  | Preliminary recommendations for R&D. |  |  |  | Complete review of US/Japan alternatives |  |  |  | Complete review of US/Japan alternatives
2005 | Feb |  |  |  |  | SPL vs RCS: define comparative study | [5 empty] | tests of mercury target |  | solenoid or/and beam together
2005 | Mar |  | BENE Week | final definition of 3rd batch of TPW proposals |  | review HIPPI progress report | [6 empty] | Review results on stress resistence limit of materials |  |  | 1st International Conference on Targets and Collectors |  | Workshop: detailed comparison of frontends |  |  |  | Workshop: detailed comparison of frontends
2005 | Apr |  |  | submission of more CARE JRP's(^)? |  | accelerating structure 1, |  | Review results on stress resistence limit of materials | [5 empty] | test of granulated target |  |  | Review results on stress resistence limit of materials
2005 | May |  |  |  | "Munich report" on the same subject | elliptical cavity | [5 empty] | start design of final >4MW target | Review final design of the new prototype |  |  | Laboratory Visits by Section Cordinator |  | Review of designs with other components |  |  |  | Review of designs with other components
2005 | Jun |  | NuFact05 Europe | end of comparative studies | intermediate report | SPL vs RCS: preliminary conclusions |  | Review final design of the new prototype | start design of final collection |  | start design of final collection | decide if additional TPW needed | Make decision on additional TPW if needed | start design of final >4MW target | start design of final collection | Attend NuFact05 | Review final design of the new prototype | Determine R&D and other work required to | Publication of intermediate report |  |  | Determine R&D and other work required to | select & cost accelerating option
|  |  |  | road map to CDRs, 1st sets of parameters etc | preliminary road map |  |  | Make decision on additional TPW if needed | decide if additional TPW needed |  | decide if additional TPW needed | 1st International Conference on Targets and Collectors |  | decide if additional TPW needed | decide if additional TPW needed |  | Make decision on additional TPW if needed | select optimum design |  |  |  | select optimum design
2005 | Jul |  | BENE Week |  |  | review HIPPI progress report | 1st International Conference on Targets and Collectors |  |  | 1st International Conference on Targets and Collectors |  |  |  | 1st International Conference on Targets and Collectors |  |  |  | Write R&D proposals and start fundraising |  |  |  | Write R&D proposals and start fundraising
2005 | Aug |  |  |  |  | first RFQ tests, chopper design | decide if additional TPW needed | Review life time study of a 50 Hz horn |  | decide if additional TPW needed |  |  | Review life time study of a 50 Hz horn |  |  | decide if additional TPW needed | Review life time study of a 50 Hz horn
2005 | Sep |  |  |  |  | beam transport |  | addendum to CTA Proposal? | life time study of a 50 Hz horn |  | life time study of a 50 Hz horn | addendum to TTA Proposal? | addendum to CTA Proposal? |  | life time study of a 50 Hz horn |  | addendum to CTA Proposal? | select & cost accelerating option
2005 | Oct |  |  |  |  | ECR source modelisation | addendum to TTA Proposal? |  | addendum to CTA Proposal? | addendum to TTA Proposal? | addendum to CTA Proposal? |  |  | addendum to TTA Proposal? | addendum to CTA Proposal? | addendum to TTA Proposal? |  | Assess MICE usefulness for alternative frontends |  | submission of more TPW activities? | submission of more TPW activities? | Assess MICE usefulness for alternative frontends
2005 | Nov |  | BENE & CARE Week | [12 empty] | Meeting of Network Target and Collector Sections
2005 | Dec |  |  |  |  | results of the studies for most elements | [5 empty] | Publication of Conference Proceedings
2006 | Jan | [5 empty] | Publication of Conference Proceedings |  |  | Publication of Conference Proceedings |  | test of granulated target+horn |  | Publication of Conference Proceedings
2006 | Feb |  |  |  | "Valencia Workshop" on SuperBeams vs. Beta Beams vs NuFact, synergies and priorities (Valencia ?) | [8 empty] | test of granulated target+horn
2006 | Mar |  | BENE Week | [12 empty] | Meeting of Network Target and Collector Sections
2006 | Apr
2006 | May | [14 empty] | Laboratory Visits by Section Cordinator |  | Propose MICE experiments for alternative FEs |  |  |  | Propose MICE experiments for alternative FEs
2006 | Jun |  | NuFact06 USA | [8 empty] | 2nd Main meeting of the Target and Collector Sections. |  |  |  | Attend NuFact06
2006 | Jul |  | BENE Week |  |  | Driver Workshop | 2nd Main meeting of the Target and Collector Sections. |  |  | 2nd Main meeting of the Target and Collector Sections. |  | observe beam in jet & solenoid |  | 2nd Main meeting of the Target and Collector Sections.
2006 | Aug | [12 empty] | observe beam in jet & solenoid
2006 | Sep |  |  |  | "Valencia report" on the same subject | [6 empty] | interim report on Target and Collector developments.
2006 | Oct | [5 empty] | interim report on Target and Collector developments. |  |  | interim report on Target and Collector developments. |  | Recommendations for future R&D. |  | interim report on Target and Collector developments.
2006 | Nov |  | BENE & CARE Week |  |  |  | Recommendations for future R&D. |  |  | Recommendations for future R&D. |  |  | Report on a specific SuperBeam solutions | Recommendations for future R&D.
2006 | Dec |  |  |  |  | revision of the R&D plans | Report on a specific SuperBeam solutions |  | Report on a specific SuperBeam solutions |  | Report on a specific SuperBeam solutions |  |  |  | Report on a specific SuperBeam solutions | Report on a specific SuperBeam solutions
2007 | Jan | [16 empty] | Workshop: preliminary R&D results |  |  |  | Workshop: preliminary R&D results
2007 | Feb
2007 | Mar |  | BENE Week | [12 empty] | 2nd International Conference on Targets and Collectors |  | First observation of cooling In MICE |  |  |  | First observation of cooling In MICE
2007 | Apr | [16 empty] | Assessment of first MICE results |  |  |  | Assessment of first MICE results
2007 | May | [14 empty] | Laboratory Visits by Section Cordinator
2007 | Jun |  | NuFact07 Japan | [8 empty] | 2nd International Conference on Targets and Collectors |  |  |  | Attend NuFact07
2007 | Jul |  | BENE Week |  |  | Driver Workshop | 2nd International Conference on Targets and Collectors |  |  | 2nd International Conference on Targets and Collectors |  |  |  | 2nd International Conference on Targets and Collectors |  |  |  | Workshop: overall optimisation of NF design |  |  |  | Workshop: overall optimisation of NF design
2007 | Aug
2007 | Sep |  |  |  | A report on an optimized parameter list for SB, BB and NF. Addressing the problems of systematic errors | [12 empty] | Detailed assessment of MICE results |  |  |  | Detailed assessment of MICE results
2007 | Oct
2007 | Nov |  | BENE & CARE Week | [12 empty] | Meeting of Network Target and Collector Sections
2007 | Dec |  |  |  |  | revision of the R&D plans | [5 empty] | Publication of Conference Proceedings
2008 | Jan | [5 empty] | Publication of Conference Proceedings |  |  | Publication of Conference Proceedings |  |  |  | Publication of Conference Proceedings |  |  |  | Workshop: select optimal NuFact design |  |  |  | Workshop: select optimal NuFact design
2008 | Feb | [5 empty] | Report on specific NuFact solutions |  | Report on specific NuFact solutions |  | Report on specific NuFact solutions | chapter for CDR | chapter for CDR |  | Report on specific NuFact solutions | Report on specific NuFact solutions
2008 | Mar |  | BENE Week | Define general final report | Define chapter for final report |  | Define chapter for final report |  | chapter for CDR |  | chapter for CDR |  |  | chapter for CDR | chapter for CDR | Meeting of Target and Collector Sections. Define chapters for final report |  | Define chapter for final report | Define chapter for final report |  |  | Write chapter for CDR
2008 | Apr
2008 | May | [14 empty] | Laboratory Visits by Section Cordinator
2008 | Jun |  | NuFact08 Europe | present draft of BENE final report | present draft of BENE final report | present draft of final chapter | present draft of final chapter | [8 empty] | Attend NuFact07 |  | present draft of final chapter | present draft of final chapter
2008 | Jul |  | BENE Week |  |  | Driver Workshop | 3rd Main and final meeting of the Target and Collector Sections |  |  | 3rd Main and final meeting of the Target and Collector Sections |  |  |  | 3rd Main and final meeting of the Target and Collector Sections
2008 | Aug
2008 | Sep
2008 | Oct
2008 | Nov |  | BENE & CARE Week | [8 empty] | Final report and recommendations of the Target and Collector Sections |  |  |  | Meeting of Network Target and Collector Sections
2008 | Dec |  |  | end of NA: final reports and general report | final "roadmap report" | final report, driver TDR | Final report and recommendations of the Target and Collector Sections |  |  | Final report and recommendations of the Target and Collector Sections |  |  |  | Final report and recommendations of the Target and Collector Sections
road map to future
2009 | Jan
2009 | Feb
2009 | Mar |  | BENE Week
2009 | Apr
2009 | May
2009 | Jun | [18 empty] | end of DS, after 1 year of consolidation | end of DS
& maybe work towards a TDR
|  | * | Neutrino Beam Instrumentation Workshop, rotates yearly
|  | + | Feasibility Study (paperwork)
|  | ° | Technical Preparatory Work (R&D)
|  | ^ | Joint Research Project. Must be worded in terms of improvements of existing facilities
[6 empty] | Spring 2004 | Initial meeting of the Target and Collector Sections. Allotment of specific duties. |  |  | Initial meeting of the Target and Collector Sections. Allotment of specific duties. |  |  |  | Initial meeting of the Target and Collector Sections. Allotment of specific duties.
[6 empty] | Summer 2004 | 1st Main Meeting (with international participants) to present the current progress in target and collector studies. |  |  | 1st Main Meeting (with international participants) to present the current progress in target and collector studies. |  |  |  | 1st Main Meeting (with international participants) to present the current progress in target and collector studies.
[6 empty] | Winter 2004 | Publication of the current position of target and collector development. |  |  | Publication of the current position of target and collector development. |  |  |  | Publication of the current position of target and collector development.
Preliminary recommendations for future R&D.
[6 empty] | Summer 2005 |  |  | 1st International Conference on Targets and Collectors. |  | 1st International Conference on Targets and Collectors. |  |  |  | 1st International Conference on Targets and Collectors.
[6 empty] | Spring 2006 |  |  | Publication of Conference Proceedings. |  | Publication of Conference Proceedings. |  |  |  | Publication of Conference Proceedings.
[6 empty] | /Summer |  |  | 2nd Main meeting of the Target and Collector Sections. |  | 2nd Main meeting of the Target and Collector Sections. |  |  |  | 2nd Main meeting of the Target and Collector Sections.
[6 empty] | Autumn 2006 | Publication of interim report on Target and Collector developments. |  |  | Publication of interim report on Target and Collector developments. |  |  |  | Publication of interim report on Target and Collector developments.
[18 empty] | Recommendations for future R&D. |  |  |  | Recommendations for future R&D.
[6 empty] | Summer 2007 |  |  | 2nd International Conference on Targets and Collectors. |  | 2nd International Conference on Targets and Collectors. |  |  |  | 2nd International Conference on Targets and Collectors.
[6 empty] | Spring 2008 |  |  | Publication of Conference Proceedings. |  | Publication of Conference Proceedings. |  |  |  | Publication of Conference Proceedings.
[6 empty] | /Summer | 3rd Main and final meeting of the Target and Collector Sections. |  |  | 3rd Main and final meeting of the Target and Collector Sections. |  |  |  | 3rd Main and final meeting of the Target and Collector Sections. |  | 3rd Main and final meeting of the Target and Collector Sections.
[6 empty] | Winter 2008 | Final report and recommendations of the Target and Collector Sections |  |  | Final report and recommendations of the Target and Collector Sections |  |  |  | Final report and recommendations of the Target and Collector Sections |  | Final report and recommendations of the Target and Collector Sections