## Sheet1
|  | TARGET | COLLECTOR
2003 | Feb
2003 | Mar |  | Initiate Web Site creation
2003 | Apr | review tagert studies | review present horn studies
Check particle collection simulation software
2003 | May |  | Propose horn material study
Propose mechanical/thermal and power supply studies
2003 | Jun | identify final 4MW target design team
2003 | Jul | proposal for target test prototype | Propose to define a road map on experimental program
2003 | Aug | start Target test area desing | Initiate horn test area study
2003 | Sep |  | Make status report on power supply design
2003 | Oct |  | Make status report on mechanical/thermal study
2003 | Nov | check compatibility with collector exp. prog | Propose compatibility checking with TARGET program
2003 | Nov |  | Initiate a proposal for new Horn prototype construction
integrated with the TARGET station (CTA)
2003 | Dec | Draft Proposal TTA
2004 | Jan
2004 | Feb | First meeting of Target with Collector
2004 | Mar | start construction test targets
2004 | Apr | first proposal for target/horn integration | Make status report on CERN horn prototype
2004 | May |  | Initiate report on thermal diffusion coefficient measurements
2004 | Jun |  | Review existing collection systems/new prototype first design
2004 | Jul | First Main meeting of Target and Collector
2004 | Aug |  | Collector state of the art report
2004 | Sep |  | Review of test area requirements/status report power supply
2004 | Oct | TTA proposal | Review CTA proposal
2004 | Nov
2004 | Dec | State of the art report target and collector
2005 | Jan | Preliminary recommendations for R&D.
2005 | Feb | test of granular target
2005 | Mar | tests of mercury target
2005 | Apr |  | Review results on stress resistence limit of materials
2005 | May
2005 | Jun | start design of final >4MW target | Review final design of the new prototype
|  | decide if additional TPW needed | Make decision on additional TPW if needed
2005 | Jul | 1st International Conference on Targets and Collectors
2005 | Aug
2005 | Sep |  | Review life time study of a 50 Hz horn
2005 | Oct | addendum to TTA Proposal? | addendum to CTA Proposal?
2005 | Nov
2005 | Dec
2006 | Jan | Publication of Conference Proceedings
2006 | Feb | test of granulated target+horn
2006 | Mar
2006 | Apr
2006 | May
2006 | Jun
2006 | Jul | 2nd Main meeting of the Target and Collector Sections.
2006 | Aug | observe beam in jet & solenoid
2006 | Sep
2006 | Oct | interim report on Target and Collector developments.
2006 | Nov | Recommendations for future R&D.
2006 | Dec |  | Report on a specific SuperBeam solutions
2007 | Jan
2007 | Feb
2007 | Mar
2007 | Apr
2007 | May
2007 | Jun
2007 | Jul | 2nd International Conference on Targets and Collectors
2007 | Aug
2007 | Sep
2007 | Oct
2007 | Nov
2007 | Dec
2008 | Jan | Publication of Conference Proceedings
2008 | Feb |  | Report on specific NuFact solutions
2008 | Mar | chapter for CDR | chapter for CDR
2008 | Apr
2008 | May
2008 | Jun
2008 | Jul | 3rd Main and final meeting of the Target and Collector Sections
2008 | Aug
2008 | Sep
2008 | Oct
2008 | Nov
2008 | Dec | Final report and recommendations of the Target and Collector Sections
2009 | Jan
2009 | Feb
2009 | Mar
2009 | Apr
2009 | May
2009 | Jun