## Sheet1
|  | TARGET | COLLECTOR
2003 | Feb
2003 | Feb-Mar
2003 | Mar
2003 | Mar
2003 | Mar
2003 | Apr | review tagert studies | review horn studies
2003 | May |  | start of horn material study/ power supply
2003 | Jun | identify final 4MW target design team
2003 | Jul | proposal for target test prototype | decision on experiment program
2003 | Aug | start Target test area desing | Start horn test area study
2003 | Sep |  | status report power supply design
2003 | Oct |  | status report mechanical/thermal study
2003 | Nov | check compatibility with collector exp. prog | check compatibility with target exp. prog
2003 | Nov |  | proposal of new prototype construction
2003 | Dec | Draft Proposal TTA | Draf t CTA Proposal
2004 | Jan
2004 | Feb | First meeting of Target with Collector
2004 | Mar | start construction test targets | start design final power supply
2004 | Apr | first proposal for target/horn integration | status report CERN horn prototype
2004 | May |  | report on diffusion coeff. measurements
2004 | Jun |  | review existing collection sistems/new prototype first design
2004 | Jul | First Main meeting of Target and Collector
2004 | Aug |  | Collector state of the art report
2004 | Sep |  | Review of test area requirements/status report power supply
2004 | Oct | TTA proposal | CTA proposal
2004 | Nov
2004 | Dec | State of the art report target and collector
2005 | Jan | Preliminary recommendations for R&D.
2005 | Feb | test of granular target
2005 | Mar | tests of mercury target
2005 | Apr |  | first results stress limit irradiated material
2005 | May
2005 | Jun | start design of final >4MW target | final design new prototype
|  | decide if additional TPW needed | decide if additional TPW needed
2005 | Jul | 1st International Conference on Targets and Collectors
2005 | Aug
2005 | Sep |  | life time study of a 50 Hz horn
2005 | Oct | addendum to TTA Proposal? | addendum to CTA Proposal?
2005 | Nov
2005 | Dec
2006 | Jan | Publication of Conference Proceedings
2006 | Feb | test of granulated target+horn
2006 | Mar
2006 | Apr
2006 | May
2006 | Jun
2006 | Jul | 2nd Main meeting of the Target and Collector Sections.
2006 | Aug | observe beam in jet & solenoid
2006 | Sep
2006 | Oct | interim report on Target and Collector developments.
2006 | Nov | Recommendations for future R&D.
2006 | Dec |  | Report on a specific SuperBeam solutions
2007 | Jan
2007 | Feb
2007 | Mar
2007 | Apr
2007 | May
2007 | Jun
2007 | Jul | 2nd International Conference on Targets and Collectors
2007 | Aug
2007 | Sep
2007 | Oct
2007 | Nov
2007 | Dec
2008 | Jan | Publication of Conference Proceedings
2008 | Feb |  | Report on specific NuFact solutions
2008 | Mar | chapter for CDR | chapter for CDR
2008 | Apr
2008 | May
2008 | Jun
2008 | Jul | 3rd Main and final meeting of the Target and Collector Sections
2008 | Aug
2008 | Sep
2008 | Oct
2008 | Nov
2008 | Dec | Final report and recommendations of the Target and Collector Sections
2009 | Jan
2009 | Feb
2009 | Mar
2009 | Apr
2009 | May
2009 | Jun
Initial meeting of the Target and Collector Sections. Allotment of specific duties.
1st Main Meeting (with international participants) to present the current progress in target and collector studies.
Publication of the current position of target and collector development.
1st International Conference on Targets and Collectors.
Publication of Conference Proceedings.
2nd Main meeting of the Target and Collector Sections.
Publication of interim report on Target and Collector developments.
2nd International Conference on Targets and Collectors.
Publication of Conference Proceedings.
3rd Main and final meeting of the Target and Collector Sections.
Final report and recommendations of the Target and Collector Sections